## SAP - exercício
Step 1
SAP Activate Phase | Description/ Purpose | Notes/Insights (Relating to GreenHarvest Organics)
Discover | Understand the business needs, define the project scope, and plan the implementation. | 1) Understanding Needs: GreenHarvest needs to improve inventory accuracy, track batch-level expiration dates, and automate order fulfillment to reduce stockouts and spoilage.2) Defining Scope: The project scope likely includes implementing modules like SAP S/4HANA Inventory Management, Warehouse Management, and Sales & Distribution. 3) Planning implementation: The implementation plan should consider GreenHarvest's operational schedule and minimize disruption to their distribution.
Prepare | Set up the project, conduct workshops to gather detailed requirements, and design the future solution. | 1) Mapeamento de Requisitos Específicos: Coletar requisitos operacionais para o controle de perecíveis, definindo a necessidade de estratégia FEFO e checagens de disponibilidade orientadas à data de validade. 2) Estruturação e Governança: Mobilizar a equipe do projeto (analistas de negócios, gerentes de estoque e especialistas SAP), estabelecer o ambiente inicial do sistema e definir a estratégia de dados mestre para cadastros por lote de produtos frescos.
Explore | Validate the proposed solution design through workshops, prototypes, and demonstrations. | 1) Fit-to-Standard Workshops: Demonstrate SAP S/4HANA standard processes to sales and warehouse teams, validating how the system manages order entry, batch reservation, and automated shipping. 2) Gap Identification: Assess whether standard availability checks keep pace with seasonal demand fluctuations and adjust prioritization rules for batches nearing expiration to minimize food waste.
Realize | Build and configure the SAP S/4HANA system, migrate data, and test the solution. | 1) System Configuration: Configure automatic batch determination, user-friendly SAP Fiori screens for warehouse operators, and automated workflows for confirmation, picking, packing, and shipping. 2) Migration and End-to-End Testing: Cleanse and migrate material master data and current stock balances by batch. Conduct end-to-end integration testing and User Acceptance Testing, simulating demand spikes and short shelf-life scenarios.
Deploy | Go-live with the SAP S/4HANA system, train users, and provide initial support. | 1) Training and Skill Development: Train warehouse supervisors and operators on using SAP Fiori for expiration date verification and goods issuance. 2) Cutover and Go-Live Strategy: Execute the final physical inventory data migration over the weekend to avoid disrupting the daily distribution of perishables. Launch the system with intensive support to immediately address operational questions.
Run | Provide ongoing support, maintenance, and continuous improvement of the SAP S/4HANA system. | 1) Monitoring and Continuous Improvement: Track KPIs such as spoilage reduction rates, reduction in out-of-stock incidents, and order cycle time. 2) Algorithm Optimization: Continuously adjust demand forecasting and automatic replenishment parameters based on historical data regarding weather, seasonality, and consumer preferences.
Step 2
Business Analyst Activity | Description/ Purpose | Skills Required | Potential Scenarios/Notes/Insights
Conduct Stakeholder Interviews | Meet with stakeholders to gather information about their current processes, challenges, and needs for the new system. | Communication Interpersonal skills Active listening Note-taking | Scenario: Imagine interviewing the warehouse manager at a manufacturing company implementing SAP. Notes: It would be crucial to understand their current inventory management challenges, such as inaccurate stock levels or manual processes. I'd need to ask about their pain points and what they hope to achieve with the new system. Insights: Building rapport and trust with the warehouse manager would be essential to get honest and detailed information. I'd also need to be mindful of their time and ensure the interview is well-structured and efficient.
Create Business Process Flows | Document current ("as-is") business processes and design improved ("to-be") processes for the new system. | Process mapping Business process understanding Visualization tools | Scenario: Map the manual "As-Is" workflow for order receipt and delivery, and design the automated "To-Be" workflow in SAP S/4HANA. Notes: The "To-Be" workflow must integrate real-time availability checks, automatic batch determination based on expiration dates, and the triggering of picking/shipping orders. Insights: Visualizing the elimination of manual work helps demonstrate to teams how the system will reduce delays and prevent the shipment of products nearing their expiration date.
Develop Test Cases | Design test cases to verify that the implemented solution meets requirements. | Test case design techniques Understanding of testing methodologies Analytical thinking | Scenario: Create test scenarios simulating the intake of fruit batches with short shelf lives and concurrent customer orders. Notes: Validate whether the FEFO rule automatically allocates the batch with the earliest expiration date and whether the system prevents the sale of batches that do not meet the minimum shelf-life requirements specified by the customer. Insights: Testing edge cases (such as seasonal demand spikes with low inventory levels) ensures operational stability prior to Go-Live, preventing financial losses due to spoilage.
Write Functional Specifications | Document the detailed functional requirements for the solution, specifying how the system should behave. | Technical writing Attention to detail Understanding of system functionalities | Scenario: Draft the technical specification for the Available-to-Promise (ATP) check, accounting for the perishability of fresh fruits and vegetables. Notes: Define the precise batch classification rules in SAP S/4HANA (harvest/receipt date, expiration date, exact warehouse location, and quality status). Insights: Clear specifications ensure that the SAP configuration team accurately translates GreenHarvest’s sanitary and shelf-life control requirements into the system.
Facilitate Workshops | Lead workshops with stakeholders to gather requirements, validate solutions, and obtain feedback. | Facilitation skills Communication Presentation skills | Scenario: Conduct a "Fit-to-Standard" validation workshop bringing together the shipping, sales, and IT teams. Notes: Present prototypes of user-friendly SAP Fiori screens for real-time inventory checking and demonstrate automated order picking. Insights: Actively listening to warehouse operators' concerns reduces resistance to change and allows the tool to be aligned with daily warehouse routines.
Configuration Documentation | Document the configuration settings applied to the system to meet specific needs. | Technical writing Attention to detail System configuration knowledge | Scenario: Formally document the configuration parameters applied to the Sales and Inventory/Warehouse Management (MM/WM/EWM) modules. Notes: Record the FEFO structure, goods movement types, and automatic blocking rules for expired batches. Insights: Ensuring detailed documentation is essential for ongoing maintenance and future quality audits during the SAP Activate "Run" phase.
Data Migration Preparation | Plan and prepare for the migration of existing data to the new system. | Data analysis Data migration tools knowledge Project management | Scenario: Analyze, cleanse, and structure the master data for agricultural products, suppliers, and current stock balances by batch. Notes: Remove duplicate or obsolete data and audit the expiration date of each physical batch in the warehouse prior to loading into SAP S/4HANA. Insights: The quality and accuracy of the migrated data are vital; incorrect expiration data on the first day of operations would compromise the FEFO strategy and result in immediate losses.
Step 3
Business Analyst Activity | SAP Activate Phase(s) | Description of Activity in this Phase | Supporting SAP S/4HANA Capabilities/Tools
Requirements Gathering | Discover, Prepare | Discover: Gather high-level requirements to understand GreenHarvest's needs and define the project scope (e.g., real-time inventory visibility, batch management, automated order fulfillment). Prepare: Conduct detailed workshops and interviews to gather specific requirements for inventory management, order fulfillment, reporting, etc. | • SAP S/4HANA Embedded Analytics (to analyze current data) •SAP Business Process Intelligence (to analyze current processes) •SAP Solution Manager/Cloud ALM (to document requirements
Process Mapping | Prepare, Explore | Prepare: Document GreenHarvest’s current manual and paper-based processes to identify bottlenecks in sales, inventory, and shipping. Explore: Desenhar os fluxos futuros no SAP S/4HANA, integrando regras FEFO, verificação de estoque em tempo real e automação na entrega. | • SAP Signavio / Business Process Intelligence • SAP Process Navigator (Best Practices Content) • SAP Cloud ALM (Process Authoring)
Gap Analysis | Explore | Explore: Compare GreenHarvest’s operational processes with SAP S/4HANA standard processes (Best Practices). Identify gaps such as the need for custom availability rules to account for the exact shelf life of fresh producenand propose standard solutions or customizations. | • SAP Fiori Fit-to-Standard Workshops • SAP Cloud ALM (Requirements & Notes Management) • SAP Best Practices Explorer / Process Navigator
Solution Design | Explore, Realize | Explore: Define the functional specifications and architecture of outbound flows, including automatic batch determination rules based on expiration date. Realize: Validar os detalhes da configuração dos módulos de Vendas e Estoque com a equipe técnica antes da construção do sistema. | • SAP Fiori apps (Manage Batches, Sales Order Fulfillment) • SAP Extended Warehouse Management (EWM) • SAP Cloud ALM (Solution Documentation)
Testing | Realize | Realize: Design and carry out System Integration Testing (SIT) scenarios. Validate that sales orders automatically select batches with the earliest expiration dates, prevent the sale of expired items, and trigger automated issuance and dispatch. | • SAP Test Automation Tool (SAP Cloud ALM) • SAP S/4HANA Test System / Sandbox • SAP Fiori Launchpad
Training | Realize, Deploy | Realize: Create training materials and practical manuals featuring SAP Fiori screens, focused on GreenHarvest's day-to-day warehouse and sales operations. Deploy: Conduct hands-on training sessions for warehouse operators and the sales team prior to the official launch. | • SAP Enable Now • SAP Fiori Interactive Guides • SAP Learning Hub
Change Management | Prepare, Explore, Realize, Deploy | Prepare/Explore: Map the impact of the change on employees' work (from manual paper-based processes to the automated SAP system). Realize/Deploy: Implement the communication and engagement plan to reduce resistance to the new system and ensure rapid adoption by the logistics and sales teams. | • SAP Enable Now • Pesquisas de Prontidão da Organização (Surveys) • Matriz de Impacto de Mudança (Change Impact Matrix no Cloud ALM)
Data Migration | Prepare, Explore, Realize, Deploy | Prepare/Explore: Map agricultural product records, customers, and current inventory balances by lot.Realoize/Deploy: Process and clean the data, validate physical expiration dates in the warehouse, and perform the final load of balances into SAP S/4HANA at the time of cutover. | • SAP S/4HANA Migration Cockpit • SAP Master Data Governance (MDG) • Database staging tools / Excel templates
User Acceptance Testing Support | Realize | Realize: Provide direct support to GreenHarvest key users during UAT. Log defects, address operational questions, and ensure the solution is approved by the business before moving to production. | • SAP Cloud ALM (Defect Management) • SAP Solution Manager (ITSM) • SAP Fiori User Feedback Tools